## Bid Schedule
2020 WCIND DREDGE AND EROSION CONTROL PROJECTS
Lyons Bay Navigation Channel Dredging and Snake Island Erosion Control Additions
BID SCHEDULE SUMMARY
WCIND PROJECTS in SARASOTA COUNTY
WCIND Project Number: 2020-04 / Humiston & Moore Engineers Project Number: 13-024
May 27, 2020
Item | Item | Estimated | Unit | Unit | Total
| Description | Quantity |  | Cost | Cost
1 | Mobilization and Demobilization Lyons Bay Channel Dredging | 1 | Job | Lump Sum | $___________
with Upland and Nearshore Disposal at Snake Island (see note I)
2 | Lyons Bay Channel Dredging with upland and nearshore | 7000 | CY | $________ | $___________
disposal at Snake Island Disposal (see note I)
3 | Environmental Control including Turbidity Testing and any | 1 | Job | Lump Sum | $___________
other temporary turbidity control measures (see note III)
4 | Final Grading Snake Island | 1 | Job | Lump Sum | $___________
5 | Daymarker Removal & Installation (See Note II) | 2 | Each | $________ | $___________
6 | Construction, staging prep, access and restoration (see note IV) | 1 | Job | Lump Sum | $___________
7 | Surveying including control and construction surveys | 1 | Job | Lump Sum | $___________
(Pre, post and interim as needed)
8 | Bid Bond for A | 1 | Job | Lump Sum | $___________
A | Sub-Total for Lyons Bay Dredging and Disposal (1-8): |  |  |  | $___________
9 | Additional Mobilization and Demobilization (if any) | 1 | Job | Lump Sum | $___________
Snake Island Erosion Control Additions
10 | Armor Stone (145 pcf, or higher) (See note VIII) | 500 | Tons | Lump Sum | $___________
11 | Bedding Stone (140 pcf, or higher)(See note IX) | 120 | Tons | Lump Sum | $___________
12 | Geogrid (See note V) | 2800 | sq. ft. | $________ | $___________
13 | Filter Fabric 3-ft overlap (See Note VI) | 2800 | sq. ft. | $________ | $___________
14 | Environmental Control including Turbidity Monitoring | 1 | Job | Lump Sum | $___________
(see note III)
15 | Daymarker Removal & Installation (See Note II) | 2 | Each | $________ | $___________
16 | Construction, staging prep, access and restoration | 1 | Job | Lump Sum | $___________
17 | Construction Surveys (Pre, Post and Interim) | 1 | Job | Lump Sum | $___________
18 | Bid Bond for B | 1 | Job | Lump Sum | $___________
B | Total for Erosion Control Additions (9-18): |  |  |  | $___________
C | Project Total (A+B) (See Note X) |  |  |  | $___________
Bid Schedule Summary Notes:
I. Quantity is estimated; final quantity based on results of the pre-construction survey.
II. If daymarker removal is necessary; costs include the removal of daymarker(s) replaced with new materials.
III. Includes the installation of turbidity curtains as described in the plans and specifications.
IV. Includes removal of temporary geotextile containment systems and turbidity curtains.
V. Geogrid estimated quantity based on footprint of structure not including allocation for waste, overlap, roll width, etc.
VI. Filter Fabric estimated quantity based on footprint of structure not including allocation for waste, required overlap, roll width, etc.
VII. All bid prices are for materials installed.
VIII. Armor Stone provided by WCIND, Contractor to transport to staging area, estimated quantity assuming 25% voids and 145 pcf.
IX. Bedding Stone provided by WCIND, Contractor to transport to staging area, estimated quantity assuming 25% voids and 140 pcf.
X. WCIND may select CONTRACTOR for Item A, B or both.